## Sheet1
Risk ID | Category | Risk Description | Likelihood (1–5) | Consequence (1–5) | Risk Rating | Response Strategy | Owner
R1 | Technical | AI model fails to meet accuracy benchmarks | 5 (Almost Certain) | 3 (Moderate) | 15 – High | Mitigate – iterative testing & validation | Technical Lead
R2 | Schedule | Delay in EEG hardware procurement | 4 (Likely) | 4 (Major) | 16 – Extreme | Transfer – vendor SLA & alternative suppliers | Procurement Manager
R3 | Budget | Cloud costs exceed estimates due to scaling | 3 (Possible) | 4 (Major) | 12 – High | Mitigate – apply cost monitoring & usage caps | Finance Officer
R4 | Stakeholder | Low faculty adoption of tutoring system | 2 (Unlikely) | 4 (Major) | 8 – Moderate | Mitigate – conduct workshops & user engagement | Project Manager
R5 | External | Regulatory approval delays (ethics/legal) | 3 (Possible) | 5 (Catastrophic) | 15 – High | Avoid – early engagement with regulators | Compliance Officer
R6 | Scope | Scope creep from additional requested features | 3 (Possible) | 3 (Moderate) | 9 – Moderate | Mitigate – enforce change control process | Project Manager
R7 | Technical | Integration issues between AI and dashboard | 3 (Possible) | 4 (Major) | 12 – High | Mitigate – modular development & early testing | System Architect
R8 | External | Cybersecurity breach during pilot phase | 2 (Unlikely) | 5 (Catastrophic) | 10 – High | Mitigate – robust encryption & audits | Security Officer
R9 | Training | Students struggle to adopt new system | 2 (Unlikely) | 2 (Minor) | 4 – Low | Mitigate – phased rollout & continuous support | Training Coordinator
R10 | Operational | Minor miscommunication between teams causes delays | 1 (Rare) | 2 (Minor) | 2 – Low | Accept – monitor and address if occurs | Project Manager
R11 | Operational | Occasional minor reporting errors in dashboard | 2 (Unlikely) | 1 (Insignificant) | 2 – Low | Accept – track and fix if noticed | QA Lead

## Sheet2
Consequences
|  | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Catastrophic (5)
Likelyhood | Almost Certain (5) | Moderate (5) | High (10) | High (15) | Catastrophic (20) | Catastrophic (25)
| Likely (4) | Moderate (4) | Moderate (8) | High (12) | Catastrophic (16) | Catastrophic (20)
| Possible (3) | Low (3) | Moderate (6) | Moderate (9) | High (12) | High (15)
| Unlikely (2) | Low (2) | Moderate (4) | Moderate (6) | Moderate (8) | High (10)
| Rare (1) | Low (1) | Low (2) | Low (3) | Moderate (4) | Moderate (5)

## Sheet3
Probablility | High | R9 | R6 | R2
| Medium | R10 | R4 | R1 R3 R5 R7
| Low | R11 |  | R8
|  | Low | Medium | High
Impact

## Sheet4
Period | Planned Spend | Cumulative Spend | % of Total
2025-08-01 | 20000 | 20000 | 4.2%
2025-09-01 | 30000 | 50000 | 10.4%
2025-10-01 | 40000 | 90000 | 18.8%
2025-11-01 | 40000 | 130000 | 27.1%
2025-12-01 | 40000 | 170000 | 35.4%
2026-01-01 | 45000 | 215000 | 44.8%
2026-02-01 | 45000 | 260000 | 54.2%
2026-03-01 | 45000 | 305000 | 63.5%
2026-04-01 | 40000 | 345000 | 71.9%
2026-05-01 | 35000 | 380000 | 79.2%
2026-06-01 | 30000 | 410000 | 85.4%
2026-07-01 | 25000 | 435000 | 90.6%
2026-08-01 | 20000 | 455000 | 94.8%
2026-09-01 | 15000 | 470000 | 97.9%
2026-10-01 | 10000 | 480000 | 100%
|  |  |  | Period | Cumulative Spend
|  |  |  | 2025-08-01 | 20000
|  |  |  | 2025-09-01 | 50000
|  |  |  | 2025-10-01 | 90000
|  |  |  | 2025-11-01 | 130000
|  |  |  | 2025-12-01 | 170000
|  |  |  | 2026-01-01 | 215000
|  |  |  | 2026-02-01 | 260000
|  |  |  | 2026-03-01 | 305000
|  |  |  | 2026-04-01 | 345000
|  |  |  | 2026-05-01 | 380000
|  |  |  | 2026-06-01 | 410000
|  |  |  | 2026-07-01 | 435000
|  |  |  | 2026-08-01 | 455000
|  |  |  | 2026-09-01 | 470000
|  |  |  | 2026-10-01 | 480000