## OK to do this I need costs for
ID | Task Name | Duration | Assigned Resource | Assumed Labor Cost | Fixed Cost (AUD) | Total Cost (AUD)
1 | 0. NeuroAdaptive Learning in Applied Classes initiative | - | - | - | - | 480000
2 | 1.0 Project Management & Governance | - | - | - | - | 124000
3 | 1.1 Project Initiation & Approvals | 5 days | Nithish | 4000 | 0 | 4000
4 | M1: Project Charter Approved | 0 days | - | 0 | 0 | 0
5 | 1.2 Stakeholder Engagement & Reporting | 12 months | Bedict | 144000 | 0 | 144000
6 | 1.3 Risk & Ethics Oversight | 12 months | Gokhulraj | 180000 | 0 | 180000
7 | 1.4 Project Closure | 5 days | Nithish, Bedict | 7250 | 0 | 7250
8 | 2.0 Planning & Procurement | - | - | - | - | 139500
9 | 2.1 Finalise Requirements & Scope | 10 days | Nithish, Bharath | 15000 | 0 | 15000
10 | 2.2 Procure EEG Headbands (Batch 1) | 20 days | Gokhulraj | 15000 | 40000 | 55000
11 | 2.3 Procure Cloud Infrastructure | 15 days | Gokhulraj | 11250 | 15000 | 26250
12 | 2.4 Vendor Contract Negotiation | 10 days | Bedict | 6500 | 0 | 6500
13 | 2.5 Secure Ethical & Legal Approval | 20 days | Nithish, Gokhulraj | 31000 | 0 | 31000
14 | M2: Ethical Approval Secured | 0 days | - | 0 | 0 | 0
15 | 3.0 System Development & Configuration | - | - | - | - | 160500
16 | 3.1 Develop AI Dashboard (Alpha) | 30 days | Bharath | 21000 | 0 | 21000
17 | 3.1.1 User Interface Design & Wireframing | 10 days | Bharath | 7000 | 0 | 7000
18 | 3.1.2 Front-End Development | 15 days | Bharath | 10500 | 0 | 10500
19 | 3.1.3 Back-End API Development | 15 days | Gokhulraj | 11250 | 0 | 11250
20 | 3.1.4 EEG Signal Integration | 10 days | Nithish, Gokhulraj | 15500 | 0 | 15500
21 | 3.1.5 Data Anonymisation & Privacy Features | 10 days | Bharath, Gokhulraj | 14500 | 0 | 14500
22 | 3.2 Build Cloud Analytics Engine | 25 days | Nithish, Bharath | 19250 | 0 | 19250
23 | 3.2.1 Database Schema Design | 5 days | Gokhulraj | 3750 | 0 | 3750
24 | 3.2.2 AI Model Selection & Configuration | 10 days | Bharath | 7000 | 0 | 7000
25 | 3.2.3 Data Processing Logic | 10 days | Nithish | 8000 | 0 | 8000
26 | 3.3 Internal Testing & Debugging | 20 days | Nithish, Gokhulraj | 31000 | 0 | 31000
27 | 3.3.1 Unit & Integration Testing | 10 days | Gokhulraj | 7500 | 0 | 7500
28 | 3.3.2 System Bug Fixes | 10 days | Bharath | 7000 | 0 | 7000
29 | M3: System Ready for Pilot | 0 days | - | 0 | 0 | 0
30 | 4.0 Training & Change Management | - | - | - | - | 21000
31 | 4.1 Develop Tutor Training Materials | 10 days | Bedict | 6500 | 0 | 6500
32 | 4.2 Deliver Training Workshops (Cohort 1) | 10 days | Bedict, Nithish | 14500 | 0 | 14500
33 | M4: Tutor Training Complete | 0 days | - | 0 | 0 | 0
34 | 4.3 Develop Digital Adoption Guides | 5 days | Bedict | 3250 | 0 | 3250
35 | 4.4 Tutor Onboarding & Support | 2 days | Bedict | 1300 | 0 | 1300
36 | 5.0 Pilot Deployment (Phase 1) | - | - | - | - | 25750
37 | 5.1 Install EEG Devices in Pilot Units | 5 days | Nithish, Gokhulraj | 7750 | 0 | 7750
38 | 5.2 Configure IT Systems & Dashboard Access | 5 days | Bharath | 3500 | 0 | 3500
39 | M5: Pilot Deployment Begins | 0 days | - | 0 | 0 | 0
40 | 5.3 Conduct Live Pilot (Semester 1) | 3 months | All | 124000 | 0 | 124000
41 | 5.4 Provide Technical Support | 3 months | Gokhulraj | 57000 | 0 | 57000
42 | 6.0 Pilot Evaluation & Iteration | - | - | - | - | 39750
43 | 6.1 Collect Quantitative Data | 10 days | Bharath | 7000 | 0 | 7000
44 | 6.2 Conduct Qualitative Interviews & Surveys | 5 days | Bedict | 3250 | 0 | 3250
45 | M6: Data Collection Complete | 0 days | - | 0 | 0 | 0
46 | 6.3 Analyse Pilot Results vs KPIs | 15 days | Nithish, Bharath | 12750 | 0 | 12750
47 | 6.4 Implement System Iterations & Fixes | 20 days | Gokhulraj, Bharath | 29000 | 0 | 29000
48 | 6.5 Prepare Iteration Report | 5 days | Bedict | 3250 | 0 | 3250
49 | 7.0 Expansion & Scalability | - | - | - | - | 124500
50 | 7.1 Develop Expansion Plan & Budget | 10 days | Nithish, Bedict | 14500 | 0 | 14500
51 | 7.2 Procure Additional EEG Headbands (Batch 2) | 20 days | Nithish | 16000 | 20000 | 36000
52 | 7.3 Secure New Faculty Approvals | 15 days | Bedict | 9750 | 0 | 9750
53 | 7.4 Prepare New IT Infrastructure | 10 days | Gokhulraj | 7500 | 0 | 7500
54 | 7.5 Develop Training Materials for New Cohorts | 10 days | Bedict | 6500 | 0 | 6500
55 | 7.6 Conduct Pilot Rollout (Semester 2) | 5 months | All | 200000 | 0 | 200000
56 | 8.0 Project Finalisation | - | - | - | - | 33750
57 | 8.1 Final Evaluation & Reporting | 20 days | Nithish, Bedict, Gokhulraj | 32000 | 0 | 32000
58 | 8.1.1 Quantitative Impact Analysis | 10 days | Bharath | 7000 | 0 | 7000
59 | 8.1.2 Qualitative Feedback Synthesis | 10 days | Bedict | 6500 | 0 | 6500
60 | 8.1.3 Draft Final Report & Executive Summary | 5 days | Nithish, Bedict | 7250 | 0 | 7250
61 | M7: Final Report Submitted | 0 days | - | 0 | 0 | 0
62 | 8.2 Future Feature Roadmap | 15 days | Nithish, Gokhulraj | 23250 | 0 | 23250
63 | 8.3 Financial Closure & Handover | 5 days | Bharath | 3500 | 0 | 3500
64 | M8: Project Officially Closed | 0 days | - | 0 | 0 | 0